## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Notes | Date started (actual date) | Date finished (actual date)
E01 a | Check-in | Passengers can have access to all his/her flight information | very high | 1 | 1.Verify that passenger's booking number exists matching the flight information,Make sure the passenger can check-in using one's surname and ID number or scanning their ID document 2.Verify that passenger's surname and ID number and their ID document exists matching the flight information Make sure a summary of the booked flight can be displayed to the passenger Make sure the status of check-in is recorded | This is the precondition of the project and need to be throughout the entire development process | 2022-03-24 | 2022-04-14
E01 c | Select meal | Passengers are able to choose his/her meal after check-in | very high | 1 | 1.Make sure the types of meal can be displayed to the passenger 2.Verify the passenger's choices of meal is available,Make sure the passenger's choices of meal is recorded |  | 2022-03-24 | 2022-03-31
E05 a | Check Input | Passengers should receive error message if their input is invalid | very high | 1 | 1. Verify that passengers' inputs are valid Make sure the passenger know the error type if their input is invalid |  | 2022-03-24 | 2022-03-31
E05 c | Software Development | Use Java to develop the software as a stand-alone application | very high | 1 | 1.Make sure the developers use the latest Java SE(15 or above). 2.Make sure the UI only satisfies the rudimentary operations 3.Make sure that developers do not build a web-based application 3.Make sure the software to run on at least two operation systems |  | 2022-03-24 | 2022-03-31
E01 b | Select seat | Passengers are able to choose his/her seat after check-in | very high | 2 | Verify the passenger's choices of seat is available 1.Make sure the seats can be displayed to the passenger 2.Make sure the passenger's choices of seat is recorded |  | 2022-04-01 | 2022-04-14
E02 b | choose special meal | Passengers can have the chance of choosing meal with a gourmet menu | medium | 2 | 1.Make sure the special type of meal can be displayed to the passenger 2.Verify the passenger's choices of meal is available 3.Verify the passenger's choice with him/her |  | 2022-03-24 | 2022-04-14
E02 a | choose special seating | Passengers can have the chance of choosing a seat with extra legroom | medium | 2 | 1.Make sure the special type of seat can be displayed to the passenger 2.Verify the passenger's choice is available 3.Verify the passenger's choice with him/her |  | 2022-04-14 | 2022-05-13
E03a | Printing boarding pass | Passengers can get their boarding pass from the kiosk | very high | 2 | 1.Verify passengers' flight information and their information attached to this flight 2.Make sure all informations can correctly be printed out |  | 2022-04-07 | 2022-04-21
E05 b | Usability | Passengers should operate the software without training | very high | 3 | 1.Make sure the instructions are placed near the place where specific operations are needed. |  | 2022/05/13 | 2022-05-27
E03b | Carry on baggage | Passengers can get a tag from the kiosk which would attach to the carry on baggage | high | 3 | 1.Verify the passengers' number of carry on baggage from the back-end file 2.Make sure all informations can correctly be printed out 3.Verify if the passengers need any tag for their carry on baggage |  | 2022-04-14 | 2022-04-28
E03c | Check-in baggage | Passengers can be attributed to a bag drop counter | high | 3 | 1.Verify the passengers' number of check-in baggage from the back-end file 2.Make sure all informations can correctly be printed out 3.Make sure the passenger can be attribute to a bag drop counter |  | 2022-04-14 | 2022-05-13
E02 c | payment | Passengers can pay for their extra options | high | 5 | 1.Make sure the passenger's choices of seat and the type of meal are recorded 2.Verify the money caused by the extra options 3.Verify the passenger's credit card exists and have enough money 4.Verify the payment of the extra options is completed |  | 2022-04-14 | 2022-04-28
E05 d | User-friendly | Passengers can operate the software smoothly | high | 5 | 1.Make sure users to cancel the operations at any time 2.Make sure the messages display promptly to the user (Maximum delay: 50ms) 3.Make sure that developers reduce all the redundancies in user interface and shows only rudimentary operations. 4.Make sure that the software allow users to backup to any step they want |  | 2022-05-13 | 2022-05-27
E05 e | Scalability | Design a flexible and extensible software | high | 5 | 1.Make sure that interfaces for new operations are reserved 2.Make sure the new operations can be added without changing the code for former operations 3.Make sure the software can customize client without redesign the framework 4.Make sure all functions and classes are encapsulated without code redundancy 5.Make sure each operation is independent from other operations. |  | 2022-05-13 | 2022-05-27
E04 | check the passengers' list | Airline managers can check the passengers’ information on any flight | medium | 5 | 1.Verify different flight number and select the passengers attached to the flight. 2.Make sure all the passenger’s check-in status being recorded by the system 3.Make sure a interface being built to send the information package to the back-end system |  | 2022-04-14 | 2022-04-21