## Sheet1
Story ID | Module | Story Name | Description | Priority | Iteration | Acceptance Criteria | Notes | Point | Date Started | Date Finished
1 | Order | Order options and add add-ons basic | As a customer I want to be free to choose and cancel options and add-ons of the foods So that I can order my own food. | very high | 1 | 1.For each option, users should be free to choose and cancel. 2.For each add-ons,users should be free to choose and cancel. 3.For each option, users must choose one.If an option are not available, it needs a prompt. | For add-ons and options, the interface should be written as extensible as possible | 5 | 2020-03-26 | 2020-03-28
6 | Order | In-store and take-out | As a customer I want to be free to choose between in-store and take-out So that I can eat more conveniently. | very high | 1 | Users can click the button to choose to eat or take away.If no one is selected, there will be a prompt to notice the user. |  | 2 | 2020-03-27 | 2020-03-27
8 | Payment | Payment interface information display(Name, quantity and unit price) | As a customer I want to know the options and add-ons' name, quantity and unit price before paying So that it is convenient for me to know the purchase details before paying. | very high | 1 | Before the user pays, the user system should diplay the selection of this transaction, the name of add-ons, unit price and quantity. |  | 3 | 2020-03-26 | 2020-03-27
9 | Payment | Payment interface information display(total price) | As a customer I want to know the total price before paying So that it is convenient for me to know the purchase details before paying. | very high | 1 | Before the user pays, the user system should diplay the total price. |  | 2 | 2020-03-28 | 2020-03-28
11 | Payment | Payment method | As a customer I want to choose Cash or Card to pay So that I can pay the foods more easliy. | very high | 1 | 1.Before payment, the user should be able to see the two buttons clearly. 2.If no one is selected, there will be a prompt to notice the user. |  | 2 | 2020-03-29 | 2020-03-29
14 | Payment | Ticket basic | As a chef I want to see the options and add-ons which customers choose So that I can make ramen to satisfy customers. | very high | 1 | Options and add-ons which customers choose should be shown in the ticket |  | 3 | 2020-03-27 | 2020-03-28
16 | Management | Modify price(ramen) | As a restaurant owner I want have the operating authorization of the price So that I can change the food price with the market requirement and make the best menu | very high | 1 | 1.The change of the price can be saved and displayed correctly on the machine 2. There will be an alert if the user input the non-numeric character. 3.Before save the change, the program should conduct secondary confirmation to alert the administrator | The first iteration did not consider the GUI | 5 | 2020-03-27 | 2020-03-29
17 | Management | Modify options(available) | As a manager I want to make certain options and add-ons unavailable through the admin system So that in some cases, the customer will not be able to choose a dish that is not available | very high | 1 | 1.The button of add-on or the option can be unavailable by the management system (different from the situation of unavailable products) 2.After each modification, it's a pormpt for administrator to comfirm | The first iteration did not consider the GUI | 3 | 2020-03-29 | 2020-03-30
7 | Order | Number of add-ons | As a customer I want be free to choose the number of add-ons So that I can order easily and quickly. | high | 2 | 1.Each add-ons can be unselected by the user. 2. Each add-ons should have an upper limit on the number to be selected.The user cannot select an add-ons over its maximum limited. 3. The add-ons maximum limited should be able to be modified in the management system | This content is related to the management system | 3 | 2020-04-10 | 2020-04-11
10 | Payment | Loyalty selection | As a customer I want to choose one of the three buttons for login, registration and direct payment on the payment interface just before paying So that I can choose to register as a new member or login to an existing member or not become a member to pay directly. | very high | 2 | 1.After confirming the options and add-ons, the user should see three prominent buttons. 2.Click the three buttons to log in, register and pay directly |  | 8 | 2020-04-11 | 2020-04-14
12 | Payment | Stamp display | As a loyal customer I want to view my stamps when I successfully log in or register So that I can always know the number of the stamps. | high | 2 | 1.There should be a special graphical interface to show the number of stamps 2. The user can enter this page through a button after logging in. |  | 5 | 2020-04-13 | 2020-04-14
13 | Payment | Stamps for free meal | As a restaurant owner I want to have a prompt for getting a free meal when the collected stamps reaches 10(not include add-ons) So that more consumers will consume my restaurant. | high | 2 | 1. Before the user selects the method of payment, the user should get a prompt if he gets 10 stamps 2.The prompt should contain information about the stamps and a confirmation button. When the user clicks the confirmation button, 10 stamps will be deducted automatically and the ramen is free(not include add-ons). 3.If the user chooses some add-ons and has 10 stamps, he still gets paid.Because he needs to pay extra for add-ons | This process may need to be optimized in the future | 5 | 2020-04-11 | 2020-04-13
15 | Payment | Ticket ID | As a restaurant owner I want that each ticket has an unique number and the ticket genration time So that I can process orders according to the time of purchase | very high | 2 | 1.each ticket should have a separate number that increments from 1. 2. Each ticket should specify the time the order was created. The format of time is yyyy:MM:dd:hh:mm:ss |  | 3 | 2020-04-13 | 2020-04-14
18 | Others | Cancel Operation | As a customer I want to cancel my operation at any time and go back to previous steps So that I can correct previous mistakes at any time | very high | 2 | 1.Backing to previous steps can be achived at every step 2.Customer can back to home page at every step |  | 2 | 2020-04-12 | 2020-04-12
19 | Payment | Stamp collection | As the owner of the restaurant I want that the loyal customers can get a stamp after paying so that there will be more loyal customers to come to the restaurant. | very high | 2 | 1.Stamp increases by 1 every time 2. Stamp will not increase by the free meal |  | 2 | 2020-04-13 | 2020-04-14
20 | Loyalty | Loyalty customer registration | As a restaurant owner I want the customer can use phone number or e-mail to register to join the loyalty scheme, and there name can be recorded So that I can have the customer's information. | very high | 2 | 1.It will be buttons to let the customer choose register after they choose add-ons. 2.The user system needs input fields that allows users to enter their first and last name 3. The user system needs a button that allows the user to choose whether to register using a phone number or an E-mail |  | 5 | 2020-04-12 | 2020-04-14
21 | Loyalty | Loyalty number | As a restaurant owner I want each loyalty customer has an unique loyalty number so that they can use the number to enjoy the restaurant, which will make my restaurant popular | very high | 2 | Number is made up of 8 digits, increasing from 0. Less than 8 bits are filled with 0, such as 00011234. |  | 3 | 2020-04-12 | 2020-04-14
22 | Management | Daily sales | As a manager I want to know how many foods have been sold each day in total So that I can prepare the meal in advance | very high | 2 | 1.The data of daily sales is cleared every 24h or 1 week 2.The total sales volume can be displayed correctly and only on the management system |  | 3 | 2020-04-14 | 2020-04-15
29 | Others | Seperated Management System | As a restaurant manager I want the management system is sperated from the main system. They use config file to communicate So that I manage the program much easier | medium | 2 | 1. The management system must also have a GUI interface 2. The management system can read and modify the config file, and the main system can read the config file. |  | 13 | 2020-04-11 | 2020-04-15
30 | Others | Config file | As a restaurant manager I want the management system can save the config into a file So that I manage the program much easier | high | 2 | 1. The management system can change and save the file. 2. The main system can read the config |  | 5 | 2020-04-12 | 2020-04-14
4 | Order | Add-ons recommendation | As a restaurant owner I want the user system to recommend customers who do not choose any add-ons to choose add-ons So that I can make more money. | medium | 3 | 1.If the user does not select any add-ons, he should receive an obvious prompt when submitting the order(before before choosing in-store or take-out).The prompt should include an add-on recommendation, along with a prominent "add" button. 2. The recommended add-on is random | If we have enough time, we can use the algorithm to rewrite the recommendation system | 2 | 2020-04-24 | 2020-04-25
5 | Order | Information display | As a restaurant owner I want the user system can display the latest information of the restaurant So that I can inform customers about the content of the restaurant and make more money. | high | 3 | 1.Before the user selects options, the system will scroll to display the latest information of the restaurant. 2. The administrator can change the content in the management system | This content is related to the management system | 3 | 2020-04-25 | 2020-04-26
23 | Others | Login or register Format Checking | As a system user I want to get prompt from the system when my input format is wrong So that I can know and correct my mistake in time | very high | 3 | 1.Make sure it works on all the inputs: price , username , password and other possible inputs 2.Make sure to give clear and corresponding prompt 3.Make sure any wrong inputs won’t pass |  | 2 | 2020-04-26 | 2020-04-26
31 | Order | Automatic exit | As a restaurant manager I want the system automatically returns to the home page for a period of time after the last customer has left So that the users can use the system more easily | medium | 3 | 1. The management system can change the time. |  | 2 | 2020-04-24 | 2020-04-25
2 | Order | Set meal recommedation | As a customer with choice difficulties I want the user system can recommend some set meals to me So that I can order more conveniently and quickly. | low | 4 | 1.Users are free to choose whether to buy the set meals or not 2. If the user does not choose the set meals, he must have the opportunity to choose options and add-ons freely 3. Users should be able to know the price of the set meals | This work is troublesome and requires the cooperation of multiple modules.The boss should be able to change the content and price of the package | 3 | 2020-05-09 | 2020-05-10
41 | Management | Set meal recommedation change | As a manager I want to change the set meals which are recommended to the customers So that I can make more profit by sellig the set meal | low | 4 | 1.A set meal contains options and add-ons 2.The set meals will be displayed on the user page |  | 2 | 2020-05-09 | 2020-05-09
24 | Others | Extensibility | As a restaurant owner I want the system can change dishes'name So that I can use the system in different restaurants and markets | medium | 4 | 1.User can initialize the system easily 2. Each dishes'name can be changed. |  | 2 | 2020-05-09 | 2020-05-09
25 | Management | Time period statistics | As a manager I want to see the total quantity of the sales each day or week So that I can make a better calculation | low | 4 | The data of daily sales is cleared every 24h or 1 week |  | 3 | 2020-05-09 | 2020-05-10
3 | Order | Spicy warning | As a customer I want the user system can warn me when I choose "max spicy" So that I can avoid very spicy noodles. | very low | 4 | 1.The user should see a clear warning prompt after selecting 2. After clicking "confirm", users can continue to choose options |  | 1 | 2020-05-10 | 2020-05-10
27 | Management | View popularity of spiciness | As a manager who like spicy food I want to see the sales of each spiciness level So that I can know that which spiciness is the most popular among people and enjoy the meal | very low | 4 | The data need to be shown in the management system. |  | 2 | 2020-05-10 | 2020-05-10
28 | Others | Operating Instruction | As a customer I want the system can give simple operating instructions when necessary So that I can use the system more easily | very low | 4 | 1.Make sure the instructions are user-friendly 2.There could be a question mark at the upper right corner at every page which is needed. |  | 3 | 2020-05-10 | 2020-05-11
32 | Others | Code Readability | As a software engineer I want the code of the system can be read easily So that I can understand and then updatae the system easily | very high | 5 | 1.The code can be understand easily 2.Make sure there are enough comments and javadoc |  | 8 | 2020-05-10 | 2020-05-15
34 | Management | Operation Alert | As a manager I want to see the alert when I make some mistakes during I adjust the price or else So that I can correct it immediatily | medium | 5 | A window alert can be display when the operation goes wrong |  | 2 | 2020-05-19 | 2020-05-19
38 | Others | Time Out | As a manager I want the system can return the first page automatically if the customer stop operating it So that the next customer can use it from the first page | high | 4 | The ordering process can return to the welcome page automatically after 120s without operation |  | 3 | 2020-05-20 | 2020-05-21
35 | Management | Report generation | As a manager I want to generate the report of the weekly sales So that I can know more about the situations of the restaurant | medium | 5 | The report is about weekly sales |  | 5 | 2020-05-19 | 2020-05-21
36 | Management | Report generate automatically | As a manager I want to generate the report automatically on Monday each week So that I can know more about the situations of the restaurant | low | 5 | Reports are automatically generated every Monday morning when the administrator sets up automatic generation. |  | 3 | 2020-05-19 | 2020-05-20
40 | Management | Sales information statistics | As a manager I want to know the sales condition of sales for one day, one month and one week, such as total sales volume, average unit price, etc So that I can know more about the situations of the restaurant | low | 5 | New information entered must be validated |  | 3 | 2020-05-21 | 2020-05-22
39 | Others | Floating point filtering | As a customer I want to keep the prices of all items to two decimal places So that I can buy food more easily. | medium | 5 | Make sure you round the decimal when you keep it. No more than 2 decimal places are allowed in the system |  | 1 | 2020-05-22 | 2020-05-22